## $50 million table
Table 1.19 Capital Expenditure Projects Greater Than $50 million 1
Note: Information in bold type denotes changes from the 2011/12 second Quarterly Report.
|  |  |  | Projected |  | Total Costs | Projected | Total |  | Project Financing
|  |  |  | Completion |  | to | Costs to | Capital | Internal/ | Federal | Other
| ($ millions) |  |  | Date |  | Dec. 31, 2011 | Complete | Costs | Debt | Government | Contributions
Taxpayer-supported
School districts
| Revelstoke Elementary and Secondary ……………………………………………………………………………………………….. |  |  | Fall 2012 |  | 44 | 16 | 60 | 58 | 0 | 2
| Chilliwack Secondary ……………………………………………………………………………………………….. |  |  | Fall 2013 |  | 10 | 48 | 58 | 58 | 0 | 0
| Burnaby Central Secondary ……………………………………………………………………………………………….. |  |  | Spring 2012 |  | 44 | 16 | 60 | 60 | 0 | 0
| Centennial Secondary ……………………………………………………………………………………………….. |  |  | Fall 2014 |  | 0 | 62 | 62 | 62 | 0 | 0
| Alberni District Secondary ……………………………………………………………………………………………….. |  |  | Fall 2012 |  | 29 | 29 | 58 | 54 | 0 | 4
| Full-day kindergarten ……………………………………………………………………………………………….. |  |  | Fall 2012 |  | 99 | 35 | 134 | 134 | 0 | 0
|  | Total school districts ……………………………………………………………………………………………………….. |  |  |  | 226 | 206 | 432 | 426 | 0 | 6
Post-secondary institutions
University of British Columbia
– Pharmaceutical Sciences and Centre for Drug
|  | Research & Development ……………………………………………………………………………………………….. |  | Fall 2012 |  | 78 | 55 | 133 | 86 | 3 | 44
Health facilities
Jim Pattison Outpatient Care and Surgery Centre 2, 3
| – Government direct cost ……………………………………………………………………………………………………………………….. |  |  | Fall 2012 |  | 54 | 11 | 65 | 65 | 0 | 0
| – P3 contract ………………………………………………………………………………………………………………………………… |  |  | Spring 2011 |  | 172 | 0 | 172 | 172 | 0 | 0
Victoria Royal Jubilee Hospital – Patient Care Centre
| – Government direct cost ……………………………………………………………………………………………………… |  |  | Spring 2013 |  | 141 | 9 | 150 | 23 | 0 | 127
| – P3 contract ………………………………………………………………………………………………………………………………….. |  |  | Spring 2011 |  | 199 | 0 | 199 | 199 | 0 | 0
Fort St. John Hospital and Residential Care ………………………………………………………….
| – Government direct cost …………………………………………………………………………………………………………….. |  |  | Spring 2012 |  | 244 | 21 | 265 | 169 | 0 | 96
| – P3 contract ……………………………………………………………………………………………………………………………………………….. |  |  | Spring 2012 |  | 2 | 31 | 33 | 33 | 0 | 0
Expansions to Kelowna General and
Vernon Jubilee Hospitals
| – Government direct cost ……………………………………………………………………………………………………………….. |  |  | Spring 2012 |  | 251 | 24 | 275 | 26 | 0 | 249
| – P3 contract …………………………………………………………………………………………………………………………………………….. |  |  | Spring 2012 |  | 158 | 0 | 158 | 158 | 0 | 0
Northern Cancer Control Strategy
| – Government direct cost ……………………………………………………………………………………………………………….. |  |  | Fall 2012 |  | 59 | 32 | 91 | 87 | 0 | 4
| – P3 contract …………………………………………………………………………………………………………………………………………….. |  |  | Summer 2012 |  | 14 | 1 | 15 | 15 | 0 | 0
Lions Gate Hospital (Mental Health)
| Redevelopment 4………………………………………………………………………………………………………… |  |  | Fall 2013 |  | 0 | 58 | 58 | 34 | 0 | 24
Surrey Emergency/Critical Care Tower 5
| – Government direct cost ……………………………………………………………………………………………………………….. |  |  | Summer 2014 |  | 55 | 252 | 307 | 287 | 0 | 20
| – P3 contract …………………………………………………………………………………………………………………………………………….. |  |  | Summer 2014 |  | 53 | 126 | 179 | 179 | 0 | 0
| Interior Heart and Surgical Centre 6………………………………………………………………………………………………………… |  |  | Spring 2017 |  | 89 | 304 | 393 | 302 | 0 | 91
| Children's and Women's Hospital 7………………………………………………………………………………………………………… |  |  | Fall 2017 |  | 14 | 668 | 682 | 532 | 0 | 150
|  | Total health facilities ……………………………………………………………………………………………………….. |  |  |  | 1505 | 1537 | 3042 | 2281 | 0 | 761
Transportation
South Fraser Perimeter Road
| – Government direct cost ………………………………………………………………………………………………………….. |  |  | Summer 2014 |  | 769 | 293 | 1062 | 714 | 348 | 0
| – P3 contract …………………………………………………………………………………………………………………………………….. |  |  | Summer 2014 |  | 107 | 95 | 202 | 202 | 0 | 0
| Sierra Yoyo-Desan Road upgrade 8………………………………………………………………………………………………………………………………… |  |  | Fall 2012 |  | 77 | 60 | 137 | 137 | 0 | 0
|  | Total transportation ………………………………………………………………………………………………………… |  |  |  | 953 | 448 | 1401 | 1053 | 348 | 0
Other
| Vancouver Convention Centre expansion project ………………………………………………………………………………. |  |  | Summer 2009 | 3 | 834 | 2 | 836 | 494 | 222 | 120
| BC Place redevelopment 9………………………………………………………………………………. |  |  | Fall 2011 |  | 490 | 73 | 563 | 563 | 0 | 0
| Integrated case management system………………………………………………………………………………. |  |  | Fall 2014 |  | 95 | 87 | 182 | 179 | 3 | 0
Surrey Pretrial Service Centre expansion 10
| – Government direct cost ………………………………………………………………………………………………………….. |  |  | Fall 2013 |  | 7 | 7 | 14 | 14 | 0 | 0
| – P3 contract …………………………………………………………………………………………………………………………………….. |  |  | Fall 2013 |  | 17 | 73 | 90 | 90 | 0 | 0
| e-Health initiative 11………………………………………………………………………………………………………… |  |  | Spring 2013 |  | 242 | 20 | 262 | 138 | 124 | 0
|  | Total other ……………………………………………………………………………………………………………………………………….. |  |  |  | 1685 | 262 | 1947 | 1478 | 349 | 120
|  |  | Total taxpayer-supported ............................................................................ |  |  | 4447 | 2508 | 6955 | 5324 | 700 | 931
Table 1.19 Capital Expenditure Projects Greater Than $50 million 1 (continued)
Note: Information in bold type denotes changes from the 2011/12 second Quarterly Report.
|  |  |  | Projected |  | Total Costs | Projected | Total |  | Project Financing
|  |  |  | Completion |  | to | Costs to | Capital | Internal/ | Federal | Other
| ($ millions) |  |  | Date |  | Dec. 31, 2011 | Complete | Costs | Debt | Government | Contributions
Self-supported
Transportation
| Port Mann Bridge / Highway 1 ........................................................................................ |  |  | Winter 2013 |  | 2325 | 994 | 3319 | 3319 | 0 | 0
Power generation and transmission
BC Hydro 12
| – GM Shrum G1–G4 stator replacement ………………………………………………………………………… |  |  | Fall 2010 | 3 | 75 | 1 | 76 | 76 | 0 | 0
| – Revelstoke Unit 5 generation ………………………………………………………………………… |  |  | Fall 2010 | 3 | 242 | 7 | 249 | 249 | 0 | 0
| – Central Vancouver Island transmission line ………………………………………………………………………… |  |  | Fall 2010 | 3 | 59 | 1 | 60 | 60 | 0 | 0
| – Cheakamus spillway gate reliability upgrade ………………………………………………………………………… |  |  | Summer 2011 | 3 | 61 | 2 | 63 | 63 | 0 | 0
| – Columbia Valley transmission ………………………………………………………………………… |  |  | Fall 2012 |  | 66 | 67 | 133 | 133 | 0 | 0
| – Fort Nelson generating station upgrade 13………………………………………………………………………… |  |  | Winter 2012 |  | 154 | 9 | 163 | 163 | 0 | 0
| – Stave Falls spillway gate reliability upgrade 13………………………………………………………………………… |  |  | Winter 2013 |  | 29 | 35 | 64 | 64 | 0 | 0
| – Vancouver City Central transmission ………………………………………………………………………… |  |  | Spring 2013 |  | 80 | 97 | 177 | 177 | 0 | 0
| – Smart metering and infrastructure program ………………………………………………………………………………………. |  |  | Summer 2013 |  | 221 | 709 | 930 | 930 | 0 | 0
| – Dawson Creek area reinforcement 13………………………………………………………………………… |  |  | Fall 2013 |  | 8 | 242 | 250 | 250 | 0 | 0
| – Mica gas insulated switchgear replacement 13………………………………………………………………………… |  |  | Winter 2014 |  | 104 | 84 | 188 | 188 | 0 | 0
| – Northwest transmission line ………………………………………………………………………… |  |  | Spring 2014 |  | 62 | 499 | 561 | 234 | 130 | 197
| – Seymour Arm series capacitor 13………………………………………………………………………… |  |  | Spring 2014 |  | 1 | 99 | 100 | 100 | 0 | 0
– Hugh Keenleyside spillway gate reliability
| upgrade 13………………………………………………………………………… |  |  | Spring 2014 |  | 24 | 70 | 94 | 94 | 0 | 0
| – Interior to Lower Mainland transmission line ………………………………………………………………………… |  |  | Winter 2015 |  | 85 | 624 | 709 | 709 | 0 | 0
| – GM Shrum units 1 to 5 turbine upgrade 13………………………………………………………………………… |  |  | Spring 2015 |  | 24 | 264 | 288 | 288 | 0 | 0
| – Mica units 5 and 6 project 13………………………………………………………………………… |  |  | Fall 2015 |  | 145 | 594 | 739 | 739 | 0 | 0
| – Ruskin Dam safety and powerhouse upgrade 13 ………………………………………………………………………… |  |  | Winter 2018 |  | 65 | 715 | 780 | 780 | 0 | 0
| – Southern Interior series compensation 13………………………………………………………………………… |  |  | Fall 2018 |  | 1 | 81 | 82 | 82 | 0 | 0
| – John Hart replacement 13 ………………………………………………………………………… |  |  | TBD |  | 56 | 1294 | 1350 | 1350 | 0 | 0
Columbia River power projects 14
| – Waneta Dam power expansion ………………………………………………………………………………………. |  |  | May 2015 |  | 99 | 250 | 349 | 349 | 0 | 0
|  | Total power generation and transmission …………………………………………………………………………………………………… |  |  |  | 1661 | 5744 | 7405 | 7078 | 130 | 197
Other
British Columbia Lottery Corporation
| – Gaming management system ........................................................................................ |  |  | Winter 2015 |  | 1 | 103 | 104 | 104 | 0 | 0
Insurance Corporation of British Columbia
| – Business transformation program ........................................................................................ |  |  | Fall 2016 |  | 48 | 160 | 208 | 208 | 0 | 0
|  | Total other ……………………………………………………………………………………………………………………………………….. |  |  |  | 49 | 263 | 312 | 312 | 0 | 0
|  |  | Total self-supported ............................................................................ |  |  | 4035 | 7001 | 11036 | 10709 | 130 | 197
|  |  | Total $50 million projects ............................................................................ |  |  | 8482 | 9509 | 17991 | 16033 | 830 | 1128
1 | Only projects that receive provincial funding and have been approved by Treasury Board and/or Crown corporation boards are included in this table. Ministry service plans may include projects that still require final approval. Capital costs reflect current government accounting policy.
2 | Figures shown do not include an additional $2 million to establish an offsite access road to the facility.
3 | Assets have been put into service and only trailing costs remain.
4 | Figures shown do not include an approved project reserve of $4 million.
5 | Figures shown do not include an approved project reserve of $26 million. The Emergency Department is expected to be operational by summer 2013.
6 | Figures shown are based on preliminary Treasury Board approvals and do not include an approved project reserve of $37 million. These amounts will change after P3 contracts are finalized.
7 | Figures shown are based on preliminary Treasury Board approvals. These amounts will change after P3 contracts are finalized.
8 | Figures shown do not include a $50 million capital reserve for future oil and gas access road development in the Northern Rockies area.
9 | The BC Place redevelopment project achieved substantial completion in September 2011. Work to complete the project continued through the fall of 2011 and is expected to last until the spring of 2012. Remaining work items include completion and commissioning of the fixed and retractable roof components, various upgrades (e.g. mechanical and electrical upgrades), and resolution of any contractor claims.
10 | Figures shown do not include an approved project reserve of $9 million.
11 | The e-Health initiative is comprised of 7 distinct projects. Figures shown reflect the total costs of the 7 Ministry of Health's provincially co-ordinated e-Health projects. The federal government portion is an estimate based on a signed agreement with Canada Health Infoway and the actual amount may vary, depending on eligible project costs incurred.
12 | BC Hydro has restated the capital cost of a number of its projects to conform with the move to International Financial Reporting Standards. For further details, please see Appendix I of the F2012-F2014 Amended Revenue Requirements Application currently before the BC Utilities Commission.
13 | Total costs and completion dates for these projects vary depending on the final scope. Information shown represents current assumptions.
14 | Joint ventures of the Columbia Power Corporation and Columbia Basin Trust. In October 2010, CPC/CBT reached an agreement for a partnership with Fortis Inc. to develop an electricity generating facility at the Waneta Dam south of Trail. Capital spending information reflects 49 per cent of the total project – CPC's 32.5 per cent share combined with CBT's 16.5 per cent share.